## Offer v1
Taskbreakdown for Colosseum Dental
Contact person: Becze Szabolcs
Email: becze.szabolcs@sonrisa.hu
Phone: +40 740 507 135
Tasks | Effort (days)
| Min. | Max.
Already done Aug - October
Investigating file transformation workflow failures and design a solution | 10 | 10
Status Update failing to call tracking table (table scalability issue) - Set Entry | 0.5 | 0.5
File transformation function further investigation | 4 | 4
Increase INT17 filefetcher trigger to avoid fludding | 0.5 | 0.5
Release version: PR 773,803,804 | 3 | 3
Short term plans/suggestion
New Issue: Performance bottleneck on outbound integration trigger
Making outbound integration trigger separate for each integration | 2 | 4
New issue: INT02 bankStmtImport bad call for failed file transformation to Status Update
Fix logical error in Status Update call | 1 | 2
File transformation asynchronous pattern turn off (has to be tested with large files) | 3 | 5
Set retry for Function App call | 1 | 2
Long term plans/suggestion
New Issue: Status Update failing to call tracking table (table scalability issue)
Completed records stored in separate tables | 6 | 11
New Issue: Status Update failing due to not finding files
Adding error handling to workflow (if file is already at the destination only tries to update table) | 4 | 6
Tracking should only be done by table (long term solution - SSOT) | 8 | 12
Total (Days) | 43 | 60